## Sheet1
Product backlog ID | Story | Tasks | Started Tasks | Done | Assigned to
10 | Main UI | Implement login in database | X |  | Cian
|  | Login GUI | X |  | Michael
11 | Setup Rest API for data retreival | Setup a Java Class to Consume the API |  | X | Cian
1 | The user must be able to add projects. | GUI |  | X | Dylan
|  | -Add name | X
|  | -Add individuals | X
|  | -Add end date | X
2 | Must be able to add individuals. | GUI |  | X
|  | -Add name |  |  | Michael
-Attach to none,one or many projects
3 | Must be able to attach indviduals to projects. |  | X |  | Darragh
4 | The user must be able to scan and identify a barcode identifying an object. | GUI |  | X | Dylan
|  | search for barcode & return object | X
5 | Abiility to Assign object either to an individual or a project. | GUI
Assign object implementation
-if assigned -> project, make a person responsible
6,7,8 | Search for objects by date/ (individual/project)as of a date | GUI
-search by a date -> return all objects to be reclaimed by that date
-search by individual & date ->return all objects as of a date
-search by project & date ->return all objects as of a date
9 | Design database | Adjust to product backlog changes | X |  | Cian
|  | Complete stage one of product backlog |  | X