## Product Backlog
ID | Priority | Story | Notes
1
1 | 5 | The user must be able to add projects. Each project has a name, individuals attached to it and an end date
2 | 6 | Must be able to add individuals. Each individual has a name. An individual may be attached to none, one or many projects
3 | 7 | Must be able to attach indviduals to projects.
4 | 8 | The user must be able to scan and identify a barcode identifying an object.
5 | 9 | Abiility to Assign object either to an individual or a project. If assigned to a project, then a person from the project must be made responsible for the object.
6 | 10 | The user must be able to enter a date and the project must be able to generate a list of objects that must be re-claimed by that date.
7 | 11 | The user must be able to generate a list of objects attached to an individual or a project as of a user specified date.
8 | 12 | The user must be able to scan an object already in the system and identify the individual or project it is assigned to. If assigned then identify the individual responsible for the object.
9 | 4 | Design and create database for the project
10 | 13 | Main UI Activity that provide access to the other features
11 | 3 | Setup Rest API spec for data retreival
12 | 2 | Activity Diagrams and Design the App
13 | 1 | Research and familiarise with the required technologies

## Completed stories
ID | Importance | Story | Notes | How to demo | Status | Points

## Parking lot
ID | Importance | Story | Notes | How to demo | Status | Points

## Sprint 1 Retrospective example
Team Member | Set the Stage (how did you feel this sprint) | What Happend this sprint | Why did those things happen | What To Do to keep up what worked well and prevent what didn't
Joy |  | started with blank slate - started with user input and opportunity to understand the blueprint and define the development environment and tools | did a good job at detailing out tasks | keep up with task list
Amanda | waiting to run | figured out target audience and how we will serve their needs | got a good handle on what we need to build | strategically manage wider group of stakeholders with Howard - maybe do a phase feature presentation with wider group
Jeff |  | well prepared to utilize the services from DEP | focus on who is going to use it | refer back to the interview outputs - use them to feed future stories
Alex | Set the stage | Sprint 0 duration was good | good at sharing info with full team
Sara | well-informed | gelled as a team | active conversations - in basecamp, and smaller mtgs on the side | dedicated conference line helps - keep it
Rob | Built solid foundation

## Sprint 1 tasks remaining ex
| Sprint Goal: Complete Sprint 3 stories including stories 32, 33, 36 (18 pts) |  |  | Planned tasks | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | Tasks remaining | #REF! | #REF! | #REF! | #REF! | #REF! | 17 | #REF! | 13 | 10 | 0
Task ID | Task | Assigned to | Status | Date/complete on | 2012-05-09 | 2012-05-10 | 2012-05-11 | 2012-05-14 | 2012-05-15 | 2012-05-16 | 2012-05-17 | 2012-05-18 | 2012-05-21 | 2012-05-22
S32 | As a marketing user I'd like to navigate BPN via faceted browse to view the Click/pick a Solution ->Click/pick Imperative(s) -> Click/pick Capabilitie(s) -> Click/view Offerings relationship.
| Create sample data which allow to demo the above steps | Dev | done |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Fill in sample data with dummy titles to reflect BP as much as possible | Dev + Bonnie | done |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Provide design and ux direction as needed | Liz + Bonnie | In progress |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
S33 | As a sales user I'd like to navigate BPN via faceted browse to view the Click/pick an Industry->Click/pick Client Owner(s) -> Click/pick Imperative(s) -> Click/view Capabilities relationship.
| Create sample data which allow to demo the above steps | Dev | done |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Fill in sample data with dummy titles to reflect BP as much as possible | Dev + Bonnie | done |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Provide design and ux direction as needed | Liz + Bonnie | in progress |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
S36 | Remaining faceted browse work
| faceted selector/filters | Guojian | done |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| faceted results | Guojian |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| faceted data integration (faked - real data not available) | Guojian | done |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| revise specs | liz | done |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hand off revised specs and assets | liz | done |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| review animations, coded interaction design | liz, bonnie, goujian | In progress |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| make any requested revisions to animations, interaction design | goujian, liz, bonnie | In progress |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
S37a | Server side Applicaiton Framework to host WI integration
| Create Spring based application | Umesh | Done |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Add Spring MVC for various flows | Umesh | Done |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Add Spring Security as authentication front door | Umesh | Done |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create Custom Authentication provider to integrate with Matt Stokes REST Service | Umesh | Done |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Integrate Custom Authentication provider | Umesh | Done |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Integrate with Faceted browse functionality created by Guojian | Umesh | Done |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Apply HTTPS & Deploy on bprint.webmaster.ibm.com server | Umesh | In Progress |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
S37 | WI Framework Prep
| Requested Application Server from Brian | Umesh | done |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Submit BTMT Record | Jennifer | Done |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Begin Prep GCRB APD (this is the architecture documentation) | Umesh /Till |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Configure app server (base framework for auth mechanism) |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Review Design with Jeff | Till | Done |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Present | Test / Deploy / Feature Presentation
| Unit Test |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Push code for team testing |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Team / Prod Owner UAT |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Testing Revisions |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Final production deploy of code |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Feature Presentation Prep |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Prod Owner Acceptance |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | 17 | #REF! | 13 | 10 | 0
ID | Impediments list | Assigned to | Status