## Product Backlog
ID | Priority | Story | Notes | Person Responsible
1
9 | 3 | Design and Create a database for the project |  | Cian
11 | 2 | Setup Rest API for data retreival |  | Cian
13 | 1 | Research and familiarise with the required technologies |  | Team
4 | 8 | The user must be able to scan a barcode identifying an object |  | Dylan

## Completed stories
ID | Importance | Story | Notes | How to demo | Status | Points

## Parking lot
ID | Importance | Story | Notes | How to demo | Status | Points

## Sprint 1 Retrospective example
Team Member | Set the Stage (how did you feel this sprint) | What Happend this sprint | Why did those things happen | What To Do to keep up what worked well and prevent what didn't
Joy |  | started with blank slate - started with user input and opportunity to understand the blueprint and define the development environment and tools | did a good job at detailing out tasks | keep up with task list
Amanda | waiting to run | figured out target audience and how we will serve their needs | got a good handle on what we need to build | strategically manage wider group of stakeholders with Howard - maybe do a phase feature presentation with wider group
Jeff |  | well prepared to utilize the services from DEP | focus on who is going to use it | refer back to the interview outputs - use them to feed future stories
Alex | Set the stage | Sprint 0 duration was good | good at sharing info with full team
Sara | well-informed | gelled as a team | active conversations - in basecamp, and smaller mtgs on the side | dedicated conference line helps - keep it
Rob | Built solid foundation

## Sprint 1 tasks remaining ex
| Sprint Goal: Complete Sprint 3 stories including stories 32, 33, 36 (18 pts) |  |  | Planned tasks | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  |  | Tasks remaining | #REF! | #REF! | #REF! | #REF! | #REF! | 17 | #REF! | 13 | 10 | 0
Task ID | Task | Assigned to | Status | Date/complete on | 2012-05-09 | 2012-05-10 | 2012-05-11 | 2012-05-14 | 2012-05-15 | 2012-05-16 | 2012-05-17 | 2012-05-18 | 2012-05-21 | 2012-05-22
S32 | As a marketing user I'd like to navigate BPN via faceted browse to view the Click/pick a Solution ->Click/pick Imperative(s) -> Click/pick Capabilitie(s) -> Click/view Offerings relationship.
| Create sample data which allow to demo the above steps | Dev | done |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Fill in sample data with dummy titles to reflect BP as much as possible | Dev + Bonnie | done |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Provide design and ux direction as needed | Liz + Bonnie | In progress |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
S33 | As a sales user I'd like to navigate BPN via faceted browse to view the Click/pick an Industry->Click/pick Client Owner(s) -> Click/pick Imperative(s) -> Click/view Capabilities relationship.
| Create sample data which allow to demo the above steps | Dev | done |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Fill in sample data with dummy titles to reflect BP as much as possible | Dev + Bonnie | done |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Provide design and ux direction as needed | Liz + Bonnie | in progress |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
S36 | Remaining faceted browse work
| faceted selector/filters | Guojian | done |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| faceted results | Guojian |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| faceted data integration (faked - real data not available) | Guojian | done |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| revise specs | liz | done |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| hand off revised specs and assets | liz | done |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| review animations, coded interaction design | liz, bonnie, goujian | In progress |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| make any requested revisions to animations, interaction design | goujian, liz, bonnie | In progress |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
S37a | Server side Applicaiton Framework to host WI integration
| Create Spring based application | Umesh | Done |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Add Spring MVC for various flows | Umesh | Done |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Add Spring Security as authentication front door | Umesh | Done |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Create Custom Authentication provider to integrate with Matt Stokes REST Service | Umesh | Done |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Integrate Custom Authentication provider | Umesh | Done |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Integrate with Faceted browse functionality created by Guojian | Umesh | Done |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Apply HTTPS & Deploy on bprint.webmaster.ibm.com server | Umesh | In Progress |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
S37 | WI Framework Prep
| Requested Application Server from Brian | Umesh | done |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Submit BTMT Record | Jennifer | Done |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Begin Prep GCRB APD (this is the architecture documentation) | Umesh /Till |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Configure app server (base framework for auth mechanism) |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Review Design with Jeff | Till | Done |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Present | Test / Deploy / Feature Presentation
| Unit Test |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Push code for team testing |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Team / Prod Owner UAT |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Testing Revisions |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Final production deploy of code |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Feature Presentation Prep |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Prod Owner Acceptance |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
[5 empty] | #REF! | #REF! | #REF! | #REF! | #REF! | 17 | #REF! | 13 | 10 | 0
ID | Impediments list | Assigned to | Status