## Sheet1
Risk | Probability | Impact | Exposure | Action | Person
Too little time to complete project | 20% | 8 | 1.6 | Daily meetings to ensure we are keeping to schedule | Group
Too much time spent dedicated to learning basic android development | 40% | 7 | 2.8 | Extra meetings to help each other with android dev | Group
Failing to deliver sprint cycle deliverables for cycle 1 | 10% | 3 | 0.3 | - | -
Failing to deliver sprint cycle deliverables for cycle 2 | 15% | 3 | 0.45 | - | -
Failing to deliver sprint cycle deliverables for cycle 3 | 25% | 3 | 0.75 | - | -
Failure to deliver final product | 10% | 10 | 1 | - | -